## Sheet1
Job | Complete | Notes | Person
Updated Website |  |  | Max
Game Executable
Uploaded on Website
Executable Test Plan | S
Uploaded on Website
Test Plan Results | S
Uploaded on Website
User Manual | S
Editable Source Uploaded
Pdf Uploaded
Change Report
Formal approach to change management | y |  | James/Max?
Includes change management of Documentation | y
Includes change management of code | y
Updated Testing Report | S |  | Peter
Includes precise URLs
Explained in report
Updated Methods and Plans | y |  | James/Max
Development Methods and Tools
Team Management Approaches
Plan for Assessment 4 | S
Includes precise URLs
Implementation
Four Fire Engines | Y | Added fire engines to the array list and calculated positon of where it should begin. Fully Fucntional. | Jack
Six Fortresses | Y |  | James/Jack
Patrols | S
Should find the Fire Engine after a period of time | Y |  | Jack
Minigame | Y |  | Peter
Documented Code | Y
Comments should outline new sections of code | Y
Executable JAR
Zipfile linked
Implementation Report |  |  | James/Max?
Explain how code implements architecture
Explain how code implements requirements
Briefly explain significant new features
Systematic report of significant changes
Statement of non-implemented features